## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status | Dependencies | Milestones?
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | Jane Doe | Completed |  | Yes
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 days | John Smith | In Progress | Project Initiation | Yes
Design Phase | 2024-04-11 | 2024-05-30 | 50 days | Lisa Chen | Not Started | Requirements Gathering | Yes
Development Phase | 2024-06-01 | 2024-08-31 | 90 days | Team A (Dev) | Not Started | Design Phase | No
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 65 days | Team B (QA) | Not Started | Development Phase | Yes
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | 25 days | IT Operations | Not Started | Testing & Quality Assurance | Yes
Post-Implementation Review | 2024-11-01 | 2024-11-30 | 30 days | Project Manager | Not Started | Deployment & Go-Live | Yes