## Worksheet
Task | Start Date | End Date | Responsible Person | Status
Project Initiation | 2024-01-01 | 2024-01-15 | John Smith | Completed
Scope Definition | 2024-01-16 | 2024-02-05 | Sarah Johnson | In Progress
Risk Assessment | 2024-02-06 | 2024-02-15 | Mike Davis | Planned
Resource Allocation | 2024-02-16 | 2024-03-01 | Lisa Brown | Not Started
Project Planning | 2024-03-02 | 2024-03-31 | Tom Wilson | Planned
Execution Phase | 2024-04-01 | 2024-06-30 | Team A & B | Not Started