## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Dependencies
Project Initiation | 01/01/2024 | 01/15/2024 | John Doe | Completed | -
Feasibility Study | 01/16/2024 | 02/05/2024 | Jane Smith | In Progress | Project Initiation
Requirement Gathering | 02/06/2024 | 03/15/2024 | Mike Johnson | Planned | Feasibility Study
Design Phase | 03/16/2024 | 05/10/2024 | Sarah Lee | Not Started | Requirement Gathering
Development & Testing | 05/11/2024 | 08/30/2024 | David Kim | Planned | Design Phase
Deployment & Go-Live | 09/01/2024 | 09/30/2024 | Lisa Wong | Not Started | Development & Testing
Post-Implementation Review | 10/01/2024 | 10/31/2024 | Robert Brown | Planned | Deployment & Go-Live