## Worksheet
Activity | Start Date | End Date | Responsible Party | Status | Key Deliverable
Project Initiation | 2024-03-01 | 2024-03-15 | Project Manager | Completed | Feasibility Study & Scope Approval
Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | Finalized Requirements Document
Design Phase | 2024-04-11 | 2024-05-15 | UI/UX Design Team | Not Started | Wireframes & UX Prototypes
Development Phase | 2024-05-16 | 2024-08-31 | Engineering Team | Planned | Functional Application Build
Testing & QA | 2024-09-01 | 2024-10-15 | QA Team | Not Started | Bug Fixes & Performance Validation
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | Operations Team | Planned | System Live & User Training Complete
Post-Launch Support & Review | 2024-11-01 | 2024-12-31 | Support & Project Office | Not Started | Performance Metrics Report & Feedback Collection