## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | Project Manager | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 days | Business Analysts | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 days | UX & UI Team | Planned
Development | 2024-05-16 | 2024-07-31 | 76 days | Software Developers | Not Started
Testing & QA | 2024-08-01 | 2024-08-31 | 31 days | QA Team | Not Started
Deployment | 2024-09-01 | 2024-09-15 | 15 days | IT Operations | Planned
Post-Deployment Review | 2024-09-16 | 2024-09-30 | 15 days | Project Manager & Stakeholders | Not Started