## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | John Doe | In Progress
Scope Definition | 2024-01-16 | 2024-02-01 | 16 days | Jane Smith | Not Started | Project Initiation
Resource Planning | 2024-02-02 | 2024-02-15 | 14 days | Mike Johnson | Not Started | Scope Definition
Risk Assessment | 2024-02-16 | 2024-03-01 | 16 days | Sarah Lee | Not Started | Resource Planning
Development Phase | 2024-03-02 | 2024-05-31 | 91 days | Team A | Not Started | Risk Assessment
Testing & QA | 2024-06-01 | 2024-07-15 | 45 days | Alex Brown | Not Started | Development Phase
Deployment | 2024-07-16 | 2024-07-31 | 16 days | Chris Wilson | Not Started | Testing & QA
Post-Deployment Review | 2024-08-01 | 2024-08-15 | 15 days | All Team Members | Not Started | Deployment