## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Milestones | Resources Required | Risk Level
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Jane Doe | Completed |  | Initiation Approved | Project Charter, Stakeholder List | Low
Requirements Gathering | 2024-01-16 | 2024-02-14 | 30 | John Smith | In Progress | Project Initiation |  | Stakeholder Interviews, Workshops | Medium
Design Phase | 2024-02-15 | 2024-03-31 | 48 | Lisa Wong | Planned | Requirements Gathering | UI/UX Design Approved | Wireframes, Prototypes | Medium
Development Phase | 2024-04-01 | 2024-06-30 | 91 | Mike Brown | Not Started | Design Phase |  | Developers, QA Team, Cloud Services | High
Testing Phase | 2024-07-01 | 2024-07-31 | 31 | Sarah Lee | Planned | Development Phase | System Test Passed | Unit Tests, Integration Tests, UAT | Medium
Deployment & Go-Live | 2024-08-01 | 2024-08-15 | 15 | David Kim | Not Started | Testing Phase | Go-Live Successful | IT Team, Operations Team | Low
Post-Implementation Review | 2024-08-16 | 2024-08-31 | 16 | All Project Team | Planned |  | Review Report Submitted | Feedback, Lessons Learned | Low