## Worksheet
Activity | Start Date | End Date | Duration (Days) | Budget (USD) | Status | Responsible Party
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | 50,000 | On Track | Project Director
Feasibility Study | 2024-03-16 | 2024-04-10 | 35 | 75,000 | On Track | Business Analysts
Requirements Gathering | 2024-04-11 | 2024-05-30 | 60 | 120,000 | On Track | Requirements Team
Design & Prototyping | 2024-06-01 | 2024-07-15 | 55 | 180,000 | On Track | Design Lead
Development Phase | 2024-07-16 | 2024-10-31 | 116 | 950,000 | On Track | Engineering Team
Testing & QA | 2024-11-01 | 2024-12-15 | 60 | 150,000 | On Track | QA Manager
Deployment & Launch | 2024-12-16 | 2024-12-31 | 16 | 80,000 | On Track | Operations Lead
Post-Launch Review | 2025-01-01 | 2025-01-31 | 31 | 45,000 | Pending | Project Manager