## Worksheet
Task | Start Date | End Date | Responsible | Status | Duration (Days)
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | John Smith | Completed | 1
Requirements Gathering | 2024-04-02 | 2024-04-10 | Lisa Chen | In Progress | 9
Design Phase | 2024-04-11 | 2024-04-25 | Mike Rivera | Planned | 15
Development Phase | 2024-04-26 | 2024-05-31 | Sarah Kim | Not Started | 36
Testing & QA | 2024-06-01 | 2024-06-15 | David Park | Planned | 15
Client Review & Approval | 2024-06-16 | 2024-06-18 | Client Team | Not Started | 3
Deployment & Go-Live | 2024-06-19 | 2024-06-19 | Admin Team | Planned | 1
Post-Go-Live Support | 2024-06-20 | 2024-07-15 | Support Team | Not Started | 26