## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Duration (Days)
Project Initiation | 2024-03-01 | 2024-03-07 | Jane Smith | Completed | 7
Scope Definition | 2024-03-08 | 2024-03-15 | John Doe | In Progress | 7
Stakeholder Meetings | 2024-03-16 | 2024-03-22 | Lisa Chen | Completed | 7
Work Breakdown Structure (WBS) | 2024-03-23 | 2024-03-30 | Michael Ross | Planned | 7
Risk Assessment | 2024-04-01 | 2024-04-08 | Sarah Lee | Not Started | 7