## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Priority | Milestone?
Project Initiation & Feasibility Study | Jan 05, 2024 | Jan 18, 2024 | Project Director | On Track | High | Yes
Stakeholder Requirements Gathering | Jan 19, 2024 | Feb 05, 2024 | Business Analysts | On Track | High | No
Project Scope & Budget Finalization | Feb 06, 2024 | Feb 15, 2024 | Finance & Project Manager | On Track | High | Yes
Development Phase Planning | Feb 16, 2024 | Mar 03, 2024 | Engineering Lead | On Track | Medium | No
Design & Prototyping | Mar 04, 2024 | Mar 25, 2024 | UI/UX Team | On Track | High | Yes
Development & Coding | Mar 26, 2024 | May 15, 2024 | Software Developers | On Track | High | No
Testing & Quality Assurance | May 16, 2024 | Jun 05, 2024 | QA Team | On Track | High | Yes
User Training & Documentation | Jun 06, 2024 | Jun 20, 2024 | Training Coordinator | On Track | Medium | No
Go-Live & Deployment | Jun 21, 2024 | Jun 28, 2024 | IT Operations | On Track | High | Yes
Post-Implementation Review & Reporting | Jul 01, 2024 | Jul 10, 2024 | Project Manager | On Track | Medium | No