## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Remarks
Project Initiation | 2024-01-01 | 2024-01-15 | John Doe | Completed | Feasibility study and stakeholder alignment.
Requirements Gathering | 2024-01-16 | 2024-02-15 | Jane Smith | In Progress | Interviews with key users and business teams.
Design Phase | 2024-02-16 | 2024-03-31 | Mike Johnson | Planned | UI/UX wireframes and system architecture.
Development | 2024-04-01 | 2024-06-30 | Sarah Lee | Not Started | Core functionality coding and integration.
Testing & QA | 2024-07-01 | 2024-07-31 | David Brown | Not Started | Unit, integration, and user acceptance testing.
Deployment | 2024-08-01 | 2024-08-15 | Lisa Chen | Not Started | Go-live in production environment.
Post-Implementation Review | 2024-08-16 | 2024-08-31 | Project Manager | Not Started | Gather feedback and document lessons learned.