## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status | Dependencies
Project Initiation | 2024-01-15 | 2024-01-20 | 5 days | John Smith | Completed | -
Requirements Gathering | 2024-01-21 | 2024-02-10 | 30 days | Lisa Chen | In Progress | Project Initiation
Design Phase | 2024-02-11 | 2024-03-15 | 45 days | Michael Ross | Not Started | Requirements Gathering
Development Phase | 2024-03-16 | 2024-05-31 | 75 days | Team A (Dev) | Not Started | Design Phase
Testing & QA | 2024-06-01 | 2024-06-30 | 30 days | Sarah Kim | Not Started | Development Phase
Deployment & Launch | 2024-07-01 | 2024-07-15 | 15 days | Operations Team | Not Started | Testing & QA
Post-Launch Review | 2024-07-16 | 2024-07-31 | 15 days | John Smith | Not Started | Deployment & Launch