## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | Completed
Scope Definition & Stakeholder Analysis | 2024-03-16 | 2024-04-05 | 21 | Business Analyst | In Progress
Requirements Gathering & Documentation | 2024-04-06 | 2024-05-10 | 35 | Requirements Team | Not Started
Design Phase (UI/UX & Technical Architecture) | 2024-05-11 | 2024-06-15 | 45 | Design Team | Not Started
Development & Coding Phase | 2024-06-16 | 2024-08-31 | 76 | Development Team | Not Started
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 56 | QA Team | Not Started
Deployment & Go-Live | 2024-10-16 | 2024-10-31 | 16 | IT Operations | Not Started
Post-Launch Review & Feedback Collection | 2024-11-01 | 2024-11-30 | 30 | Project Manager & Stakeholders | Not Started