## Worksheet
Activity | Start Date | End Date | Duration | Responsible Party | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | Project Director | Completed
Feasibility Study | 2024-03-16 | 2024-04-10 | 35 days | Business Analysts | In Progress
Requirements Gathering | 2024-04-11 | 2024-05-15 | 45 days | Stakeholder Team | Planned
Design Phase | 2024-05-16 | 2024-06-30 | 45 days | UX & Development Team | Not Started
Development & Coding | 2024-07-01 | 2024-08-31 | 60 days | Development Team | Planned
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 45 days | QA Team | Not Started
Deployment & Launch | 2024-10-16 | 2024-10-31 | 15 days | IT Operations Team | Planned
Post-Launch Review | 2024-11-01 | 2024-11-15 | 15 days | Project Director & Stakeholders | Not Started