## Worksheet
Quarter | Project Phase | Key Activities | Start Date | End Date | Responsible Team | Milestones
Q1 | Initiation & Planning | Scope definition, stakeholder analysis, risk assessment | Jan 1, 2024 | Mar 31, 2024 | Project Office & Strategy Team | Finalized project charter; Approved scope document
Q2 | Design & Development | Wireframing, UI/UX development, system architecture | Apr 1, 2024 | Jun 30, 2024 | Product & Engineering Team | Completed design mockups; Prototype approved
Q3 | Testing & Quality Assurance | Unit testing, integration testing, user acceptance testing | Jul 1, 2024 | Sep 30, 2024 | QA & Operations Team | All test cases passed; UAT signed off
Q4 | Deployment & Closure | System rollout, training sessions, post-launch review | Oct 1, 2024 | Dec 31, 2024 | Operations & Support Team | Go-live completed; Project closure report submitted