## Worksheet
Activity | Start Date | End Date | Responsible Party | Status | Milestones
Project Initiation | 2024-03-01 | 2024-03-15 | Project Manager | Completed | Kickoff Meeting, Budget Approval
Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | Requirement Review, Stakeholder Sign-off
Design Phase | 2024-04-11 | 2024-05-05 | UX & Systems Design Team | Planned | Wireframes Finalized, Design Approval
Development Phase | 2024-05-06 | 2024-07-15 | Engineering Team | Not Started | Code Review, Unit Testing Phase
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | QA Team | Not Started | Bug Fixing, UAT Completion
Deployment & Go-Live | 2024-08-11 | 2024-08-15 | IT Operations | Not Started | System Launch, Training Initiation
Post-Implementation Review | 2024-08-16 | 2024-08-31 | Project Management Team | Not Started | Performance Evaluation, Lessons Learned