## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation | Jan 1, 2024 | Jan 7, 2024 | John Doe | Completed
Scope Definition | Jan 8, 2024 | Jan 15, 2024 | Jane Smith | In Progress
Resource Planning | Jan 16, 2024 | Jan 22, 2024 | Mike Johnson | Planned
Milestone Review Meeting | Jan 23, 2024 | Jan 23, 2024 | Team Lead | Scheduled
Execution Phase Start | Jan 24, 2024 | Feb 10, 2024 | All Team Members | Not Started