## Worksheet
Phase | Start Date | End Date | Responsible Team | Key Deliverables | Milestones
Discovery & Planning | Jan 10, 2024 | Feb 5, 2024 | Product & Strategy Team | Market research, UX audit, business model | Final product vision approved
Product Design | Feb 6, 2024 | Mar 15, 2024 | Design & UX Team | Wireframes, UI mockups, design system | Design review and stakeholder sign-off
Development (Phase 1) | Mar 16, 2024 | May 30, 2024 | Engineering Team | Core features MVP built | MVP delivered and tested
Development (Phase 2) | Jun 1, 2024 | Aug 30, 2024 | Engineering Team | Advanced features, integrations | Feature complete & QA passed
Testing & Quality Assurance | Sep 1, 2024 | Oct 15, 2024 | QA & Operations Team | Bug fixes, performance tests | No critical bugs found
Launch & Go-to-Market | Oct 16, 2024 | Nov 30, 2024 | Marketing & Sales Team | Full product launch, user onboarding | First month engagement report published