## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-01-15 | 2024-01-20 | 5 days | John Doe | Completed
Requirements Gathering | 2024-01-21 | 2024-02-10 | 30 days | Jane Smith | In Progress
Design Phase | 2024-02-11 | 2024-03-15 | 45 days | Mike Johnson | Planned
Development Phase | 2024-03-16 | 2024-05-31 | 75 days | Team A | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-07-15 | 45 days | Lisa Brown | Planned
Deployment & Launch | 2024-07-16 | 2024-07-31 | 15 days | David Lee | Not Started
Post-Launch Review | 2024-08-01 | 2024-08-15 | 15 days | All Team Members | Planned