## Worksheet
Task | Start Date | End Date | Responsible Team Member | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-15 | Project Manager | Completed | -
Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | Project Initiation
Design Phase | 2024-04-11 | 2024-05-05 | UI/UX Design Team | Planned | Requirements Gathering
Development Phase | 2024-05-06 | 2024-07-15 | Software Developers | Not Started | Design Phase
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | QA Team | Not Started | Development Phase
Deployment & Launch | 2024-08-11 | 2024-08-31 | DevOps & Operations | Not Started | Testing & QA
Post-Launch Review | 2024-09-01 | 2024-09-15 | Project Manager & Stakeholders | Not Started | Deployment & Launch