## Worksheet
Task | Start Date | End Date | Status | Responsible Person | Progress (%) | Dependencies
Project Initiation | 2024-01-01 | 2024-01-15 | Completed | John Doe | 100%
Requirements Gathering | 2024-01-16 | 2024-02-15 | In Progress | Jane Smith | 65% | Project Initiation
Design Phase | 2024-02-16 | 2024-03-31 | Not Started | Alex Johnson | 0% | Requirements Gathering
Development Phase | 2024-04-01 | 2024-06-30 | Not Started | Team A | 0% | Design Phase
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | Not Started | Sarah Lee | 0% | Development Phase
Deployment & Launch | 2024-08-16 | 2024-08-31 | Not Started | Mike Brown | 0% | Testing & Quality Assurance