## Worksheet
Week | Project Phase | Key Milestones | Responsible Team | Start Date | End Date | Status | Notes / Risks
Week 1 | Project Kickoff & Planning | Finalize project charter, assign roles | Project Management Office (PMO) | 2024-04-01 | 2024-04-07 | Completed | No significant risks identified.
Week 2 | Requirements Gathering | Finalize user stories and acceptance criteria | Business Analysis Team | 2024-04-08 | 2024-04-14 | In Progress | Stakeholder feedback pending.
Week 3 | Design & Wireframing | Complete UI/UX mockups and design reviews | Design Team | 2024-04-15 | 2024-04-21 | Planned | Waiting on final stakeholder approval.
Week 4 | Development Sprint 1 | Build core features and API integrations | Engineering Team | 2024-04-22 | 2024-04-28 | Scheduled | Resource allocation confirmed.
Week 5 | Testing & QA Phase | Execute unit and integration tests | QA Team | 2024-04-29 | 2024-05-05 | Planned | Defect tracking system initialized.
Week 6 | Deployment Readiness | Prepare UAT and staging environment | Operations & DevOps Team | 2024-05-06 | 2024-05-12 | Scheduled | Final documentation to be reviewed.