## Worksheet
Project Name | Project Owner | Start Date | End Date | Status | Budget (USD) | Current Phase | Progress (%) | Risk Level | Next Milestone
Website Redesign | Sarah Johnson | 2024-03-01 | 2024-06-30 | On Track | 50,000 | Design & Development | 75% | Medium | Launch by May 15
Mobile App Launch | Mike Chen | 2024-04-10 | 2024-08-31 | In Progress | 120,000 | Beta Testing | 45% | High | User Feedback by May 30
ERP System Upgrade | Lisa Rodriguez | 2024-05-01 | 2024-11-30 | Planning | 350,000 | Requirements Gathering | 20% | Low | Finalize Scope by June 15
Marketing Campaign 2024 | David Kim | 2024-06-01 | 2024-10-31 | Scheduled | 85,000 | Pre-Launch Strategy | 30% | Medium | Content Finalized by July 10