## Worksheet
Project Name | Project Manager | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Priority Level | Scope Description | Milestones | Risk Assessment | Dependencies | Responsible Team | Communication Plan | Progress (%) | Next Review Date
Client Onboarding Platform v2.0 | Sarah Johnson | 2024-03-15 | 2024-06-30 | On Track | 500,000 | 385,250 | High | Develop and deploy a full client onboarding experience with automated workflows. | Launch MVP (March 31), User Testing (April 15), Final Deployment (June 30) | Data security risks; mitigated with encrypted storage and access controls. | IT Infrastructure Team, DevOps | Bi-weekly syncs with stakeholders via Zoom and email updates. | 78% | 2024-05-15
Market Expansion into EU | David Kim | 2024-04-01 | 2024-09-30 | Planning | 750,000 | 125,400 | Medium | Establish local presence in Germany and France through partnerships and digital marketing. | Market research (April 20), Partner selection (May 10), Launch campaign (July 1) | Regulatory compliance; legal review in progress. | Legal Team, Marketing | Monthly strategy calls with regional leads. | 35% | 2024-06-15
Internal Process Automation | Lisa Chen | 2024-05-01 | 2024-11-30 | In Progress | 450,000 | 215,670 | High | Automate invoicing, approvals, and reporting for HR and finance departments. | Approval flow design (May 15), Pilot run (June 1), Full rollout (November 1) | System downtime during integration; contingency plan in place. | Finance & HR Teams | Daily stand-ups and weekly progress reports. | 62% | 2024-08-15