## Worksheet
Project Name | Project Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Notes
Project Alpha | John Doe | 2024-01-15 | 2024-06-30 | On Track | 150,000 | 125,000 | 83% | Complete Phase 2 by May 15 | Design finalized, development ongoing
Project Beta | Jane Smith | 2024-03-01 | 2024-09-30 | In Progress | 200,000 | 145,000 | 72% | Final testing by August 1 | User feedback collected, adjustments in progress
Project Gamma | Mike Johnson | 2024-02-10 | 2024-11-30 | Planning | 300,000 | -- | 15% | Scope defined by April 1 | Feasibility study completed, team assigned