## Worksheet
Project Name | Project Code | Start Date | End Date | Budget (USD) | Actual Spend (USD)% | Status | Owner | Current Phase | Progress (%)
Client Onboarding Platform | PM-2024-001 | 2024-03-15 | 2024-07-30 | $150,000 | $128,500 (86%) | On Track | Sarah Thompson | Development Phase | 82%
Cloud Migration Initiative | PM-2024-002 | 2024-04-01 | 2024-11-30 | $350,000 | $295,400 (84%) | On Track | James Lee | Migration Phase | 76%
AI Analytics Dashboard | PM-2024-003 | 2024-05-10 | 2025-01-31 | $475,000 | $389,200 (82%) | On Track | Lisa Chen | Design & Prototyping | 68%
Supply Chain Optimization | PM-2024-004 | 2024-06-15 | 2025-03-31 | $650,000 | $498,700 (77%) | On Track | Michael Reed | Analysis Phase | 54%