## Worksheet
Project Name | Project Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Quarterly Review Date
Digital Transformation Initiative | Sarah Johnson | 2023-04-01 | 2023-06-30 | On Track | 500,000 | 425,000 | 75% | Phase 2 Launch | 2023-06-15
Customer Experience Upgrade | Michael Chen | 2023-03-15 | 2023-09-30 | In Progress | 350,000 | 285,000 | 81% | UX Design Approval | 2023-06-15
Supply Chain Optimization | Linda Rodriguez | 2023-05-01 | 2023-08-31 | Planned | 450,000 | 0 | 0% | Vendor Assessment Phase | 2023-06-15
Product Roadmap Expansion | David Kim | 2023-04-10 | 2023-12-31 | Planning Phase | 750,000 | 0 | 15% | Feature Prioritization Meeting | 2023-06-15