## Worksheet
Project Phase | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Variance % | Status | Responsible Team | Next Milestone
Initiation | 50,000 | 48,750 | +1,250 | +2.5% | On Track | Project Office | Feasibility Report Ready
Planning | 120,000 | 115,200 | +4,800 | +4.0% | On Track | Planning Committee | Scope Finalized
Execution | 300,000 | 285,600 | +14,400 | +4.8% | On Track | Operations Team | First Deliverable Published
Monitoring & Control | 80,000 | 76,200 | +3,800 | +4.75% | On Track | Project Management Office | Monthly Review Meeting
Closure | 50,000 | 49,500 | 500 | +1.0% | On Track | Closure Team | Final Audit Completed
Total Budget |  |  | +70,000 | +4.5% | Overall Project Status: On Track