## Worksheet
Task | Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Progress (%)
Project Initiation & Stakeholder Alignment | John Smith | 2024-03-01 | 2024-03-15 | In Progress | 15,000 | 8,500 | 6,500 | 56.7%
Feasibility Study & Risk Assessment | Sarah Lee | 2024-03-16 | 2024-04-05 | Pending | 10,000 | 0 | 10,000 | -
Requirements Gathering & Analysis | Michael Chen | 2024-04-062024-05-10 | Planning | 18,000 | 3,200 | 14,800 | 17.8%
Design Phase & Prototyping | Lisa Wong | 2024-05-11 | 2024-06-30 | Not Started | 35,000 | 0 | 35,000 | -
Development & Testing (Sprint 1-4) | Team A | 2024-07-01 | 2024-09-15 | Planned | 75,000 | 18,900 | 56,100 | 25.2%