## Worksheet
Project | Phase | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status | Next Milestone
Product Development | Design Phase | 50,000 | 42,500 | -7,500 (Under) | On Track | Final Design Approval - Week 8
Marketing Campaign | Launch Phase | 30,000 | 28,750 | -1,250 (Under) | On Track | First Impressions Report - Week 6
Customer Support System | Implementation Phase | 45,000 | 41,200 | -3,800 (Under) | On Track | System Go-Live - Week 12
Training Program | Preparation Phase | 15,000 | 14,500 | -500 (Under) | On Track | Training Kick-off - Week 4