## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Duration (Days)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | John Doe | Completed | 1
Requirements Gathering | 2024-03-02 | 2024-03-15 | Jane Smith | In Progress | 14
Design Phase | 2024-03-16 | 2024-04-10 | Mike Johnson | Pending | 35
Development Phase | 2024-04-11 | 2024-06-30 | Sarah Lee | Not Started | 81
Testing & QA | 2024-07-01 | 2024-07-31 | David Kim | Planned | 31
Deployment & Launch | 2024-08-01 | 2024-08-15 | Lisa Brown | Not Started | 15