## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed | 100
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analyst | In Progress | 65
Design Phase | 2024-03-16 | 2024-04-10 | 35 | UI/UX Designer | Not Started | 0
Development Phase | 2024-04-11 | 2024-06-30 | 91 | Development Team | Not Started | 0
Testing & QA | 2024-07-01 | 2024-07-31 | 31 | QA Lead | Not Started | 0
Client Review & Approval | 2024-08-01 | 2024-08-15 | 15 | Client Representative | Not Started | 0
Go-Live & Handover | 2024-08-16 | 2024-08-16 | 1 | Project Manager | Not Started | 0
Total Project Duration: |  |  | 187 days | Estimated Completion Date: |  | 2024-08-16