## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analyst | In Progress
Design Phase | 2024-03-16 | 2024-03-31 | 16 | UI/UX Designer | Planned
Development Phase | 2024-04-01 | 2024-05-31 | 60 | Development Team | Not Started
Testing Phase | 2024-06-01 | 2024-06-30 | 30 | QA Team | Planned
Deployment & Training | 2024-07-01 | 2024-07-15 | 15 | Operations Team | Not Started
Post-Implementation Review | 2024-07-16 | 2024-07-18 | 3 | Project Manager | Planned