## Worksheet
Project Phase | Start Date | End Date | Status | Responsible Team | Key Deliverables | Progress (%)
Initiation | 2024-03-01 | 2024-03-15 | Completed | Project Steering Committee | Feasibility Study, Project Charter | 100%
Planning | 2024-03-16 | 2024-04-30 | In Progress | Project Management Office (PMO) | WBS, Risk Register, Budget Plan | 65%
Execution | 2024-05-01 | 2024-08-31 | Not Started | Development & Operations Teams | Product Development, QA Testing | 0%
Monitoring & Control | 2024-05-01 | Ongoing | Ongoing | Project Manager & QA Leads | Performance Reports, Change Logs | 30%
Closure | 2024-09-01 | 2024-09-30 | Not Started | Project Closure Team | Final Report, Lessons Learned | 0%