## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status | Dependencies | Milestones | Progress (%) | Notes
PM-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | John Smith | High | Completed | - | Yes | 100% | Finalized project scope and objectives.
PM-002 | Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | High | In Progress | PM-001 | No | 65% | Client interviews completed; documentation under review.
PM-003 | Design Phase | 2024-04-11 | 2024-05-15 | 45 | Mike Chen | Medium | Not Started | PM-002 | Yes | 0% | Wireframes and UI mockups to be developed.
PM-004 | Development Phase | 2024-05-16 | 2024-08-31 | 117 | David Kim | High | Not Started | PM-003 | No | 0% | Frontend and backend coding to begin.
PM-005 | Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 60 | Lisa Wang | High | Not Started | PM-004 | Yes | 0% | Unit, integration, and UAT testing planned.
PM-006 | Deployment & Go-Live | 2024-10-16 | 2024-10-31 | 16 | James Brown | High | Not Started | PM-005 | Yes | 0% | Server deployment and user training scheduled.