## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Progress (%)
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Smith | Completed | - | 100
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | In Progress | Task 1 | 75
Design Phase | 2024-04-16 | 2024-05-05 | 21 | Mike Chen | Not Started | Task 2, Task 3 | 0
Development | 2024-05-06 | 2024-07-15 | 61 | Team A | Not Started | Task 4 | 0
Testing & QA | 2024-07-16 | 2024-08-10 | 35 | Lisa Wong | Not Started | Task 5, Task 6 | 0
Deployment | 2024-08-11 | 2024-08-15 | 5 | David Park | Not Started | Task 7 | 0
Post-Deployment Review | 2024-08-16 | 2024-08-17 | 2 | All Team | Not Started | - | 0
Total Tasks: 7 | [6 empty] | Overall Progress
Editable Schedule Planner – Project Management Template | [6 empty] | 62.5%