## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | Completed | 100% | None | All stakeholders were briefed on project goals.
Requirements Gathering | Mike Johnson | 2024-03-16 | 2024-03-31 | In Progress | 65% | Project Kickoff Meeting | Client interviews scheduled for next week.
Design Phase Planning | Sarah Lee | 2024-04-01 | 2024-04-15 | Not Started | 0% | Requirements Gathering Complete | Final design mockups to be reviewed by stakeholders.
Development Start | David Kim | 2024-04-16 | 2024-05-31 | Not Started | 0% | Design Phase Planning Complete | Front-end and back-end development to begin.
QA & Testing | Lisa Wong | 2024-06-01 | 2024-06-30 | Not Started | 0% | Development Complete | Testing to be conducted in phases with bug tracking.
Project Sign-off & Handover | Jane Smith | 2024-07-01 | 2024-07-05 | Not Started | 0% | QA & Testing Complete | Final client approval and documentation handover.