## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status | Dependencies | Milestone? | Notes
PM-0012024-03-012024-03-055John SmithHighIn ProgressYesDefine scope, objectives, stakeholders.
PM-0022024-03-062024-03-1510Sarah LeeHighNot StartedPM-001NoMeet with stakeholders to collect functional and technical requirements.
PM-0032024-03-162024-04-1035Mike ChenMediumNot StartedPM-002NoDevelop system architecture and UI mockups.
PM-0042024-04-112024-06-3091Team A (Dev)HighNot StartedPM-003NoCoding, unit testing, integration testing.
PM-0052024-07-012024-07-1515Lisa WongMediumNot StartedPM-004YesDeploy to production and conduct user training sessions.