## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Budget Allocation ($) | Current Status | Progress (%) | Forecasted Cost ($)
PM-001 | Project Initiation | 2024-03-15 | 2024-03-20 | 6 | Alice Johnson | 15,000 | Completed | 100% | 15,200
PM-002 | Feasibility Study | 2024-03-21 | 2024-04-05 | 15 | Bob Smith | 30,000 | On Track | 75% | 22,500
PM-003 | Resource Planning | 2024-04-06 | 2024-04-18 | 13 | Carol Lee | 25,000 | In Progress | 50% | 12,500
PM-004 | Design Phase | 2024-04-19 | 2024-06-30 | 73 | David Kim | 100,000 | Not Started | 0% | 105,000
PM-005 | Development & Testing | 2024-07-01 | 2024-10-31 | 122 | Eva Martinez | 350,000 | Planned | 0% | 365,000
Total Budget Allocated ($) |  |  |  |  | 520,000 | Forecasted Total Cost ($) |  |  | 527,700