## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Alex Johnson | In Progress | High
Requirements Gathering & Analysis | 2024-03-16 | 2024-04-10 | 35 | Sara Lee | On Track | Medium
Design & Prototyping | 2024-04-11 | 2024-05-05 | 35 | Mike Chen | Not Started | High
Development Phase (Frontend) | 2024-05-06 | 2024-06-15 | 40 | Lena Patel | Planned | High
Development Phase (Backend) | 2024-06-16 | 2024-07-31 | 56 | Tom Rivera | Not Started | High
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | Julia Kim | Planned | Medium
Deployment & Launch | 2024-09-01 | 2024-09-15 | 15 | Team Lead | Not Started | High
Post-Launch Review & Feedback | 2024-09-16 | 2024-10-05 | 20 | Alex Johnson | Planned | Low