## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Project Initiation | 01/01/2024 | 01/15/2024 | John Smith | Completed | 100%
Requirements Gathering | 01/16/2024 | 02/15/2024 | Sarah Lee | In Progress | 65%
Design Phase | 02/16/2024 | 03/31/2024 | Mike Chen | Not Started | 0%
Development | 04/01/2024 | 06/30/2024 | Team A | Not Started | 0%
Testing & Quality Assurance | 07/01/2024 | 08/15/2024 | Lisa Wong | Not Started | 0%
Deployment & Launch | 08/16/2024 | 08/31/2024 | Alex Rivera | Not Started | 0%
Post-Launch Review | 09/01/2024 | 09/15/2024 | Project Manager | Not Started | 0%