## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
Project Initiation & Stakeholder Alignment | Sarah Thompson | 03/05/2024 | 03/15/2024 | 10 | On Track | High | - | 90%
Requirements Gathering & Analysis | James Liu | 03/16/2024 | 04/05/2024 | 20 | On Track | High | Project Initiation & Stakeholder Alignment | 75%
Design & Prototyping Phase | Maria Gonzalez | 04/06/2024 | 05/03/2024 | 38 | On Track | Medium | Requirements Gathering & Analysis | 60%
Development & Coding | David Chen | 05/04/2024 | 07/10/2024 | 78 | On Track | High | Design & Prototyping Phase | 40%
Testing & Quality Assurance | Linda Patel | 07/11/2024 | 08/05/2024 | 35 | On Track | High | Development & Coding | 50%
Go-Live & Deployment | Robert Kim | 08/06/2024 | 08/15/2024 | 10 | Planned | High | Testing & Quality Assurance | 0%
Post-Launch Support & Feedback | Sophia Wong | 08/16/2024 | 09/30/2024 | 45 | Planned | Medium | Go-Live & Deployment | 0%