## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status | Priority | Dependencies
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Smith | Completed | High
Scope Definition | 2024-03-06 | 2024-03-15 | 10 | Lisa Chen | In Progress | High | Project Initiation
Risk Assessment | 2024-03-16 | 2024-03-20 | 5 | Mark Davis | Not Started | Medium
Resource Allocation | 2024-03-21 | 2024-03-25 | 5 | Sarah Lee | Planned | Medium | Scope Definition
Schedule Finalization | 2024-03-26 | 2024-03-31 | 6 | David Brown | Not Started | High | Risk Assessment, Resource Allocation