## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Progress (%)
PM-001 | Project Initiation & Planning | 2024-03-15 | 2024-03-25 | 10 | Jane Smith | Completed | None | 100%
PM-002 | Requirements Gathering | 2024-03-26 | 2024-04-10 | 15 | Mike Johnson | In Progress | PM-001 | 65%
PM-003 | Design Phase | 2024-04-11 | 2024-05-05 | 35 | Sarah Lee | Not Started | PM-002 | 0%
PM-004 | Development & Coding | 2024-05-06 | 2024-07-15 | 70 | David Kim | Not Started | PM-003 | 0%
PM-005 | Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | 35 | Linda Wong | Not Started | PM-004 | 0%
PM-006 | Deployment & Go-Live | 2024-08-11 | 2024-08-15 | 5 | Tom Brown | Not Started | PM-005 | 0%
Total Tasks | [7 empty] | 6