## Worksheet
Task | Responsible | Start Date | End Date | Status | Duration (Days)
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-01 | Completed | 1
Requirements Gathering | User Research Team | 2024-03-02 | 2024-03-15 | In Progress | 14
Design Phase (Wireframes) | UI/UX Designer | 2024-03-16 | 2024-03-25 | Pending | 10
Development Start | Software Team | 2024-03-26 | 2024-04-30 | Planned | 35
Testing & QA Review | QA Manager | 2024-05-01 | 2024-05-15 | Not Started | 15
User Training Sessions | Training Officer | 2024-05-16 | 2024-05-20 | Planned | 5
Go-Live Deployment | CIO / IT Lead | 2024-05-21 | 2024-05-21 | Pending Approval | 1
Post-Launch Review | Project Manager | 2024-05-22 | 2024-05-23 | Not Started | 2