## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | John Doe | Completed | None
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Jane Smith | In Progress | Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Alex Chen | Not Started | Requirements Gathering
Development Phase | 2024-04-26 | 2024-05-15 | 20 | Mike Johnson | Not Started | Design Phase
Testing & Quality Assurance | 2024-05-16 | 2024-05-30 | 15 | Sarah Lee | Not Started | Development Phase
Project Review & Delivery | 2024-06-01 | 2024-06-01 | 1 | Project Manager | Not Started | Testing & QA