## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Responsible Person | Status | Dependencies
PMT-001 | Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Doe | Completed | -
PMT-002 | <Scope Definition | 2024-04-06 | 2024-04-15 | 10 | Jane Smith | In Progress | PMT-001
PMT-003 | Resource Allocation | 2024-04-16 | 2024-04-25 | 10 | Alex Brown | Planned | PMT-002
PMT-004 | Design Development | 2024-04-26 | 2024-05-10 | 15 | Sam Wilson | Not Started | PMT-003
PMT-005 | Development & Testing | 2024-05-11 | 2024-06-15 | 45 | Mia Taylor | Not Started | PMT-004
Project Management - Schedule Planner (Planning View)