## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed | -
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analyst | In Progress | Project Kickoff Meeting
Design Phase | 2024-03-16 | 2024-03-31 | 26 | UX/UI Designer | Planned | Requirements Gathering
Development Phase | 2024-04-01 | 2024-05-31 | 60 | Development Team | Not Started | Design Phase
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | QA Engineer | Planned | Development Phase
Go-Live & Deployment | 2024-07-01 | 2024-07-05 | 5 | IT Operations | Not Started | Testing & Quality Assurance
Post-Launch Review | 2024-07-06 | 2024-07-10 | 5 | Project Manager | Planned | Go-Live & Deployment