## Worksheet
Quarter | Project Phase | Start Date | End Date | Responsible Team | Milestones | Status | Progress (%)
Q1 (Jan–Mar) | Initiation & Planning | 2024-01-01 | 2024-03-31 | Project Steering Committee | Feasibility Study Complete, Scope Finalized | On Track | 85%
Q2 (Apr–Jun) | Design & Development | 2024-04-01 | 2024-06-30 | Engineering Team | UI/UX Design Approved, Prototype Completed | On Track (with delay) | 60%
Q3 (Jul–Sep) | Testing & Validation | 2024-07-01 | 2024-09-30 | Quality Assurance Team | User Acceptance Testing (UAT) Completed, Bug Fixes Finalized | On Track | 90%
Q4 (Oct–Dec) | Deployment & Post-Launch | 2024-10-01 | 2024-12-31 | Operations & Support Team | Go-Live Scheduled, Training Delivered | <Pending Review | 20%